## Can you generate a number of st
Project | Report Date | Category | Man-Hours (Est) | Cost (€) (Est) | Man-Hours (Actual) | Cost (€) (Actual) | Key Milestone Progress / Notes
QuantumLeap - LLM for Research Summarization | 2025-03-01 | Project Management | 80 | 6.4 | 20 | 1.6 | Initial planning & team formation.
QuantumLeap - LLM for Research Summarization | 2025-03-01 | LLM Development | 300 | 24 | 20 | 4 | Base model selection & initial architecture design.
QuantumLeap - LLM for Research Summarization | 2025-03-01 | Data Engineering | 200 | 16 | 0 | 3.2 | Research paper corpus identification.
QuantumLeap - LLM for Research Summarization | 2025-03-01 | UI/UX (Mock) | 50 | 4 | 40 | 800 | Wireframing complete.
QuantumLeap - LLM for Research Summarization | 2025-03-01 | Testing & QA | 70 | 5.6 | 40 | 0 | (Not started)
QuantumLeap - LLM for Research Summarization | 2025-03-01 | Total Project Est: | 700 | 56 | 120 | 9.6 | Overall: On Track. Dataset Completion Target: 2025-05-15. Internal Alpha Testing Target: 2025-06-30.
QuantumLeap - LLM for Research Summarization | [6 empty] | Finalization Report Target: 2025-07-31.
QuantumLeap - LLM for Research Summarization | 2025-04-01 | Project Management | 80 | 6.4 | 45 | 3.6 | Regular stand-ups & stakeholder updates.
QuantumLeap - LLM for Research Summarization | 2025-04-01 | LLM Development | 300 | 24 | 60 | 9.6 | Initial fine-tuning on academic datasets.
QuantumLeap - LLM for Research Summarization | 2025-04-01 | Data Engineering | 200 | 16 | 10 | 8 | Dataset cleaning and pre-processing 50% complete.
QuantumLeap - LLM for Research Summarization | 2025-04-01 | UI/UX (Mock) | 50 | 4 | 45 | 2 | Prototype feedback loop developed.
QuantumLeap - LLM for Research Summarization | 2025-04-01 | Testing & QA | 70 | 5.6 | 10 | 800 | Basic unit testing begun.
QuantumLeap - LLM for Research Summarization | 2025-04-01 | Total Project Est: | 700 | 56 | 300 | 24 | Overall: On Track. Dataset Completion Target: 2025-05-15. Internal Alpha Testing Target: 2025-06-30.
QuantumLeap - LLM for Research Summarization | 2025-04-01 | [5 empty] | Finalization Report Target: 2025-07-31.
QuantumLeap - LLM for Research Summarization | 2025-05-01 | Project Management | 80 | 6.4 | 65 | 5.2 | Risk assessment update.
QuantumLeap - LLM for Research Summarization | 2025-05-01 | LLM Development | 300 | 24 | 70 | 17.6 | Pre-alpha model iteration #2 deployed.
QuantumLeap - LLM for Research Summarization | 2025-05-01 | Data Engineering | 200 | 16 | 100 | 13.6 | Dataset completion ~85%. Minor delays due to data source access.
QuantumLeap - LLM for Research Summarization | 2025-05-01 | UI/UX (Mock) | 50 | 4 | 48 | 3.2 | Mockups reviewed with internal stakeholders.
QuantumLeap - LLM for Research Summarization | 2025-05-01 | Testing & QA | 70 | 5.6 | 30 | 2.4 | Initial integration testing.
QuantumLeap - LLM for Research Summarization | 2025-05-01 | Total Project Est: | 700 | 56 | 525 | 42 | Overall: Minor Delay (Data Engineering). Dataset Completion Target: 2025-05-25 (revised).
QuantumLeap - LLM for Research Summarization | 2025-05-01 | [5 empty] | Internal Alpha Testing Target: 2025-07-15 (revised). Finalization Report Target: 2025-08-15 (revised).
QuantumLeap - LLM for Research Summarization | 2025-05-20 | Project Management | 80 | 6.4 | 75 | 6 | Budget review and forecast update.
QuantumLeap - LLM for Research Summarization | 2025-05-20 | LLM Development | 300 | 24 | 250 | 20 | Finalizing pre-alpha model performance.
QuantumLeap - LLM for Research Summarization | 2025-05-20 | Data Engineering | 200 | 16 | 195 | 15.6 | Dataset 95% complete. Annotation quality checks in progress.
QuantumLeap - LLM for Research Summarization | 2025-05-20 | UI/UX (Mock) | 50 | 4 | 50 | 3.6 | Frontend development on mock platform in progress.
QuantumLeap - LLM for Research Summarization | 2025-05-20 | Testing & QA | 70 | 5.6 | 40 | 3.2 | Bug fixing & initial performance tuning.
QuantumLeap - LLM for Research Summarization | 2025-05-20 | Total Project Est: | 700 | 56 | 605 | 48.4 | Overall: On Track for revised targets. Dataset Completion Target: 2025-05-25.
QuantumLeap - LLM for Research Summarization | 2025-05-20 | [5 empty] | Internal Alpha Testing Target: 2025-07-15. Finalization Report Target: 2025-08-15.
EduBot - Conversational AI for Student Support | 2025-04-05 | Project Management | 100 | 8 | 30 | 2.4 | Kick-off & requirements gathering.
EduBot - Conversational AI for Student Support | 2025-04-05 | LLM Development | 400 | 32 | 60 | 4.8 | Intent recognition module research.
EduBot - Conversational AI for Student Support | 2025-04-05 | Data Engineering | 250 | 20 | 50 | 4 | Student query log analysis begun.
EduBot - Conversational AI for Student Support | 2025-04-05 | UI/UX (Mock) | 80 | 6.4 | 15 | 1.2 | User flow mapping.
EduBot - Conversational AI for Student Support | 2025-04-05 | Testing & QA | 100 | 8 | 70 | 0 | (Not started)
EduBot - Conversational AI for Student Support | 2025-04-05 | Total Project Est: | 930 | 74.4 | 155 | 12.4 | Overall: On Track. Dataset Completion Target: 2025-06-30. Internal Alpha Testing Target: 2025-08-31.
EduBot - Conversational AI for Student Support | 2025-04-05 | [5 empty] | Finalization Report Target: 2025-10-31.
EduBot - Conversational AI for Student Support | 2025-05-05 | Project Management | 100 | 8 | 65 | 5.2 | Vendor selection for NLU tools.
EduBot - Conversational AI for Student Support | 2025-05-05 | LLM Development | 400 | 32 | 180 | 14.4 | Core dialogue management logic implemented.
EduBot - Conversational AI for Student Support | 2025-05-05 | Data Engineering | 250 | 20 | 150 | 12 | Intent/entity annotation 60% complete. Ahead of schedule.
EduBot - Conversational AI for Student Support | 2025-05-05 | UI/UX (Mock) | 80 | 6.4 | 40 | 3.2 | Conversational interface mockups approved.
EduBot - Conversational AI for Student Support | 2025-05-05 | Testing & QA | 100 | 8 | 80 | 1.6 | Initial test cases designed.
EduBot - Conversational AI for Student Support | 2025-05-05 | Total Project Est: | 930 | 74.4 | 455 | 36.4 | Overall: Ahead of Schedule (Data Engineering). Dataset Completion Target: 2025-06-15 (revised).
EduBot - Conversational AI for Student Support | 2025-05-05 | [5 empty] | Internal Alpha Testing Target: 2025-08-15 (revised). Finalization Report Target: 2025-10-15 (revised).
EduBot - Conversational AI for Student Support | 2025-05-20 | Project Management | 100 | 8 | 75 | 6 | Team capacity planning.
EduBot - Conversational AI for Student Support | 2025-05-20 | LLM Development | 400 | 32 | 210 | 16.8 | Integration with knowledge base API underway.
EduBot - Conversational AI for Student Support | 2025-05-20 | Data Engineering | 250 | 20 | 180 | 14.4 | Dataset 80% complete. Final reviews starting.
EduBot - Conversational AI for Student Support | 2025-05-20 | UI/UX (Mock) | 80 | 6.4 | 50 | 4 | Frontend component development initiated.
EduBot - Conversational AI for Student Support | 2025-05-20 | Testing & QA | 100 | 8 | 100 | 2.4 | Regression testing on dialogue flows.
EduBot - Conversational AI for Student Support | 2025-05-20 | Total Project Est: | 930 | 74.4 | 545 | 43.6 | Overall: On Track (Maintained revised schedule). Dataset Completion Target: 2025-06-15.
EduBot - Conversational AI for Student Support | 2025-05-20 | [5 empty] | Internal Alpha Testing Target: 2025-08-15. Finalization Report Target: 2025-10-15.
CodeGenius - AI-Powered Code Autocomplete | 2025-03-10 | Project Management | 60 | 4.8 | 15 | 1.2 | Initial scope definition.
CodeGenius - AI-Powered Code Autocomplete | 2025-03-10 | LLM Development | 280 | 22.4 | 40 | 3.2 | Code parsing & tokenization research.
CodeGenius - AI-Powered Code Autocomplete | 2025-03-10 | Data Engineering | 150 | 12 | 25 | 2 | Open-source code repository identification.
CodeGenius - AI-Powered Code Autocomplete | 2025-03-10 | UI/UX (Mock) | 40 | 3.2 | 5 | 400 | IDE plugin interface conceptualization.
CodeGenius - AI-Powered Code Autocomplete | 2025-03-10 | Testing & QA | 60 | 4.8 | 0 | 0 | (Not started)
CodeGenius - AI-Powered Code Autocomplete | 2025-03-10 | Total Project Est: | 590 | 47.2 | 85 | 6.8 | Overall: On Track. Dataset Completion Target: 2025-06-01. Internal Alpha Testing Target: 2025-07-31.
CodeGenius - AI-Powered Code Autocomplete | 2025-03-10 | [5 empty] | Finalization Report Target: 2025-09-30.
CodeGenius - AI-Powered Code Autocomplete | 2025-04-10 | Project Management | 60 | 4.8 | 50 | 2.4 | Stakeholder feedback incorporation.
CodeGenius - AI-Powered Code Autocomplete | 2025-04-10 | LLM Development | 280 | 22.4 | 100 | 8 | Contextual code completion model (transformer-based) initial training.
CodeGenius - AI-Powered Code Autocomplete | 2025-04-10 | Data Engineering | 150 | 12 | 70 | 5.6 | Dataset cleaning and filtering ~40% complete.
CodeGenius - AI-Powered Code Autocomplete | 2025-04-10 | UI/UX (Mock) | 40 | 3.2 | 15 | 1.2 | Mock IDE integration points defined.
CodeGenius - AI-Powered Code Autocomplete | 2025-04-10 | Testing & QA | 60 | 4.8 | 5 | 400 | Basic unit tests for parsing.
CodeGenius - AI-Powered Code Autocomplete | 2025-04-10 | Total Project Est: | 590 | 47.2 | 220 | 17.6 | Overall: On Track. Dataset Completion Target: 2025-06-01. Internal Alpha Testing Target: 2025-07-31.
CodeGenius - AI-Powered Code Autocomplete | 2025-04-10 | [5 empty] | Finalization Report Target: 2025-09-30.
CodeGenius - AI-Powered Code Autocomplete
CodeGenius - AI-Powered Code Autocomplete | 2025-05-10 | Project Management | 60 | 4.8 | 59 | 3.6 | Communication strategy updates.
CodeGenius - AI-Powered Code Autocomplete | 2025-05-10 | LLM Development | 280 | 22.4 | 180 | 14.4 | Model optimization for inference speed. Benchmarking ongoing.
CodeGenius - AI-Powered Code Autocomplete | 2025-05-10 | Data Engineering | 150 | 12 | 120 | 9.6 | Dataset 80% complete. Manual review for edge cases required more time.
CodeGenius - AI-Powered Code Autocomplete | 2025-05-10 | UI/UX (Mock) | 40 | 3.2 | 30 | 2.4 | Prototype IDE plugin developed.
CodeGenius - AI-Powered Code Autocomplete | 2025-05-10 | Testing & QA | 60 | 4.8 | 15 | 1.2 | Early performance testing. Identified minor latency issues.
CodeGenius - AI-Powered Code Autocomplete | 2025-05-10 | Total Project Est: | 590 | 47.2 | 390 | 31.2 | Overall: Minor Delay (Data Engineering, Testing). Dataset Completion Target: 2025-06-15 (revised).
CodeGenius - AI-Powered Code Autocomplete | 2025-05-10 | [5 empty] | Internal Alpha Testing Target: 2025-08-15 (revised). Finalization Report Target: 2025-10-15 (revised).
InsightFlow - AI for Sentiment Analysis of Customer Reviews | 2025-03-15 | Project Management | 70 | 5.6 | 18 | 1.44 | Project initiation and team onboarding.
InsightFlow - AI for Sentiment Analysis of Customer Reviews | 2025-03-15 | LLM Development | 250 | 20 | 160 | 3.2 | Researching sentiment analysis models and pre-trained LLMs.
InsightFlow - AI for Sentiment Analysis of Customer Reviews | 2025-03-15 | Data Engineering | 180 | 14.4 | 30 | 2.4 | Identifying customer review data sources.
InsightFlow - AI for Sentiment Analysis of Customer Reviews | 2025-03-15 | UI/UX (Mock) | 50 | 4 | 10 | 800 | Dashboard wireframes for sentiment visualization.
InsightFlow - AI for Sentiment Analysis of Customer Reviews | 2025-03-15 | Testing & QA | 60 | 4.8 | 0 | 0 | (Not started)
InsightFlow - AI for Sentiment Analysis of Customer Reviews | 2025-03-15 | Total Project Est: | 610 | 48.8 | 98 | 7.84 | Overall: On Track. Dataset Completion Target: 2025-06-15. Internal Alpha Testing Target: 2025-08-01.
InsightFlow - AI for Sentiment Analysis of Customer Reviews | 2025-03-15 | [5 empty] | Finalization Report Target: 2025-09-30.
InsightFlow - AI for Sentiment Analysis of Customer Reviews | 2025-04-15 | Project Management | 70 | 5.6 | 35 | 2.8 | Regular stakeholder meetings.
InsightFlow - AI for Sentiment Analysis of Customer Reviews | 2025-04-15 | LLM Development | 250 | 20 | 200 | 8 | Initial model fine-tuning on a small, labeled dataset.
InsightFlow - AI for Sentiment Analysis of Customer Reviews | 2025-04-15 | Data Engineering | 180 | 14.4 | 90 | 7.2 | Data ingestion pipeline established for review platforms.
InsightFlow - AI for Sentiment Analysis of Customer Reviews | 2025-04-15 | UI/UX (Mock) | 50 | 4 | 25 | 2 | Interactive dashboard prototype developed.
InsightFlow - AI for Sentiment Analysis of Customer Reviews | 2025-04-15 | Testing & QA | 60 | 4.8 | 10 | 800 | Basic unit tests for data processing.
InsightFlow - AI for Sentiment Analysis of Customer Reviews | 2025-04-15 | Total Project Est: | 610 | 48.8 | 260 | 20.8 | Overall: On Track. Dataset Completion Target: 2025-06-15. Internal Alpha Testing Target: 2025-08-01.
InsightFlow - AI for Sentiment Analysis of Customer Reviews | 2025-04-15 | [5 empty] | Finalization Report Target: 2025-09-30.
InsightFlow - AI for Sentiment Analysis of Customer Reviews | 2025-05-15 | Project Management | 70 | 5.6 | 55 | 4.4 | Risk review and mitigation strategies.
InsightFlow - AI for Sentiment Analysis of Customer Reviews | 2025-05-15 | LLM Development | 250 | 20 | 230 | 13.6 | Model performance evaluation and error analysis. Identified areas for improvement.
InsightFlow - AI for Sentiment Analysis of Customer Reviews | 2025-05-15 | Data Engineering | 180 | 14.4 | 15 | 12 | Review data processing volume increased significantly.
InsightFlow - AI for Sentiment Analysis of Customer Reviews | 2025-05-15 | UI/UX (Mock) | 50 | 4 | 40 | 3.2 | User experience feedback session with internal team.
InsightFlow - AI for Sentiment Analysis of Customer Reviews | 2025-05-15 | Testing & QA | 60 | 4.8 | 25 | 2 | End-to-end testing of data flow and sentiment output.
InsightFlow - AI for Sentiment Analysis of Customer Reviews | 2025-05-15 | Total Project Est: | 610 | 48.8 | 440 | 35.2 | Overall: Minor Delay (Model Refinement). Dataset Completion Target: 2025-06-25 (revised).
PersonaGen - AI for Synthetic Data Generation (Healthcare) | 2025-03-20 | Project Management | 90 | 7.2 | 25 | 2 | Regulatory compliance research for synthetic data.
PersonaGen - AI for Synthetic Data Generation (Healthcare) | 2025-03-20 | LLM Development | 350 | 28 | 50 | 4 | GAN/Diffusion model architecture exploration.
PersonaGen - AI for Synthetic Data Generation (Healthcare) | 2025-03-20 | Data Engineering | 220 | 17.6 | 40 | 3.2 | Accessing anonymized real patient datasets (secure environment).
PersonaGen - AI for Synthetic Data Generation (Healthcare) | 2025-03-20 | UI/UX (Mock) | 60 | 4.8 | 10 | 800 | User interface for data generation parameters.
PersonaGen - AI for Synthetic Data Generation (Healthcare) | 2025-03-20 | Testing & QA | 80 | 6.4 | 0 | 0 | (Not started)
PersonaGen - AI for Synthetic Data Generation (Healthcare) | 2025-03-20 | Total Project Est: | 800 | 64 | 125 | 10 | Overall: On Track. Dataset Completion Target: 2025-07-01. Internal Alpha Testing Target: 2025-09-01.
PersonaGen - AI for Synthetic Data Generation (Healthcare) | 2025-03-20 | [5 empty] | Finalization Report Target: 2025-11-30.
PersonaGen - AI for Synthetic Data Generation (Healthcare) | 2025-04-20 | Project Management | 90 | 7.2 | 50 | 4 | Data governance policies finalized.
PersonaGen - AI for Synthetic Data Generation (Healthcare) | 2025-04-20 | LLM Development | 350 | 28 | 150 | 12 | Initial training of generative models on small datasets.
PersonaGen - AI for Synthetic Data Generation (Healthcare) | 2025-04-20 | Data Engineering | 220 | 17.6 | 30 | 9.6 | Data anonymization and security protocols implemented.
PersonaGen - AI for Synthetic Data Generation (Healthcare) | 2025-04-20 | UI/UX (Mock) | 60 | 4.8 | 30 | 2.4 | Workflow for specifying synthetic data attributes.
PersonaGen - AI for Synthetic Data Generation (Healthcare) | 2025-04-20 | Testing & QA | 80 | 6.4 | 10 | 800 | Basic data fidelity checks on generated samples.
PersonaGen - AI for Synthetic Data Generation (Healthcare) | 2025-04-20 | Total Project Est: | 800 | 64 | 360 | 28.8 | Overall: On Track. Dataset Completion Target: 2025-07-01. Internal Alpha Testing Target: 2025-09-01.
PersonaGen - AI for Synthetic Data Generation (Healthcare) | 2025-04-20 | [5 empty] | Finalization Report Target: 2025-11-30.
PersonaGen - AI for Synthetic Data Generation (Healthcare) | 2025-05-20 | Project Management | 90 | 7.2 | 75 | 6 | External audit preparation for data security.
PersonaGen - AI for Synthetic Data Generation (Healthcare) | 2025-05-20 | LLM Development | 350 | 28 | 250 | 20 | Model refined for privacy preservation and data utility.
PersonaGen - AI for Synthetic Data Generation (Healthcare) | 2025-05-20 | Data Engineering | 220 | 17.6 | 175 | 15.2 | Scalability testing for large-scale data generation.
PersonaGen - AI for Synthetic Data Generation (Healthcare) | 2025-05-20 | UI/UX (Mock) | 60 | 4.8 | 45 | 3.6 | User feedback on generated data quality indicators.
PersonaGen - AI for Synthetic Data Generation (Healthcare) | 2025-05-20 | Testing & QA | 80 | 6.4 | 30 | 2.4 | Differential privacy evaluation begun.
PersonaGen - AI for Synthetic Data Generation (Healthcare) | 2025-05-20 | Total Project Est: | 800 | 64 | 590 | 47.2 | Overall: Ahead of Schedule. Dataset Completion Target: 2025-06-20 (revised).
PersonaGen - AI for Synthetic Data Generation (Healthcare) | 2025-05-20 | [5 empty] | Internal Alpha Testing Target: 2025-08-15 (revised). Finalization Report Target: 2025-10-31 (revised).
DocuMind - AI for Intelligent Document Processing (Invoices) | 2025-03-05 | Project Management | 80 | 6.4 | 20 | 1.6 | Requirements gathering for invoice types.
DocuMind - AI for Intelligent Document Processing (Invoices) | 2025-03-05 | LLM Development | 300 | 24 | 50 | 4 | OCR model selection and initial testing.
DocuMind - AI for Intelligent Document Processing (Invoices) | 2025-03-05 | Data Engineering | 200 | 16 | 5 | 2.4 | Collecting sample invoices (various formats).
DocuMind - AI for Intelligent Document Processing (Invoices) | 2025-03-05 | UI/UX (Mock) | 60 | 4.8 | 10 | 800 | Data extraction visualization mockups.
DocuMind - AI for Intelligent Document Processing (Invoices) | 2025-03-05 | Testing & QA | 70 | 5.6 | 0 | 0 | (Not started)
DocuMind - AI for Intelligent Document Processing (Invoices) | 2025-03-05 | Total Project Est: | 710 | 56.8 | 110 | 8.8 | Overall: On Track. Dataset Completion Target: 2025-06-10. Internal Alpha Testing Target: 2025-07-31.
DocuMind - AI for Intelligent Document Processing (Invoices) | 2025-03-05 | [5 empty] | Finalization Report Target: 2025-09-30.
DocuMind - AI for Intelligent Document Processing (Invoices) | 2025-04-05 | Project Management | 80 | 6.4 | 40 | 3.2 | Internal steering committee updates.
DocuMind - AI for Intelligent Document Processing (Invoices) | 2025-04-05 | LLM Development | 300 | 24 | 120 | 9.6 | Information extraction model (LLM-based) fine-tuning for key invoice fields.
DocuMind - AI for Intelligent Document Processing (Invoices) | 2025-04-05 | Data Engineering | 200 | 16 | 5 | 7.2 | Manual annotation of initial invoice dataset 40% complete.
DocuMind - AI for Intelligent Document Processing (Invoices) | 2025-04-05 | UI/UX (Mock) | 60 | 4.8 | 25 | 2 | Exception handling and data validation interface design.
DocuMind - AI for Intelligent Document Processing (Invoices) | 2025-04-05 | Testing & QA | 70 | 5.6 | 10 | 800 | Accuracy testing on OCR results.
DocuMind - AI for Intelligent Document Processing (Invoices) | 2025-04-05 | Total Project Est: | 710 | 56.8 | 285 | 22.8 | Overall: On Track. Dataset Completion Target: 2025-06-10. Internal Alpha Testing Target: 2025-07-31.
DocuMind - AI for Intelligent Document Processing (Invoices) | 2025-04-05 | [5 empty] | Finalization Report Target: 2025-09-30.
DocuMind - AI for Intelligent Document Processing (Invoices) | 2025-05-05 | Project Management | 80 | 6.4 | 60 | 4.8 | Resource allocation for next phase.
DocuMind - AI for Intelligent Document Processing (Invoices) | 2025-05-05 | LLM Development | 300 | 24 | 200 | 16 | Model integrated with OCR output. Performance satisfactory.
DocuMind - AI for Intelligent Document Processing (Invoices) | 2025-05-05 | Data Engineering | 200 | 16 | 10 | 12.8 | Dataset 80% complete. Minor delays due to varied invoice layouts.
DocuMind - AI for Intelligent Document Processing (Invoices) | 2025-05-05 | UI/UX (Mock) | 60 | 4.8 | 40 | 3.2 | Review and correction interface prototype.
DocuMind - AI for Intelligent Document Processing (Invoices) | 2025-05-05 | Testing & QA | 70 | 5.6 | 25 | 2 | End-to-end extraction accuracy testing. Identified edge cases.
DocuMind - AI for Intelligent Document Processing (Invoices) | 2025-05-05 | Total Project Est: | 710 | 56.8 | 485 | 38.8 | Overall: Slight Delay (Data Engineering). Dataset Completion Target: 2025-06-20 (revised).
DocuMind - AI for Intelligent Document Processing (Invoices) | 2025-05-05 | [5 empty] | Internal Alpha Testing Target: 2025-08-15 (revised). Finalization Report Target: 2025-10-15 (revised).
DocuMind - AI for Intelligent Document Processing (Invoices) | 2025-05-20 | Project Management | 80 | 6.4 | 70 | 5.6 | Budget review and risk mitigation.
DocuMind - AI for Intelligent Document Processing (Invoices) | 2025-05-20 | LLM Development | 300 | 24 | 230 | 18.4 | Error analysis and re-training on challenging invoice types.
DocuMind - AI for Intelligent Document Processing (Invoices) | 2025-05-20 | Data Engineering | 200 | 16 | 50 | 14.4 | Dataset 90% complete. Remaining invoices require complex manual annotation.
DocuMind - AI for Intelligent Document Processing (Invoices) | 2025-05-20 | UI/UX (Mock) | 60 | 4.8 | 45 | 3.6 | User training materials drafted for mock system.
DocuMind - AI for Intelligent Document Processing (Invoices) | 2025-05-20 | Testing & QA | 70 | 5.6 | 35 | 2.8 | System stability and performance testing.
DocuMind - AI for Intelligent Document Processing (Invoices) | 2025-05-20 | Total Project Est: | 710 | 56.8 | 560 | 44.8 | Overall: On Track for revised targets. Dataset Completion Target: 2025-06-20.
DocuMind - AI for Intelligent Document Processing (Invoices) | 2025-05-20 | [5 empty] | Internal Alpha Testing Target: 2025-08-15. Finalization Report Target: 2025-10-15.
VoiceVault - AI for Audio Transcription & Summarization (Meetings) | 2025-03-25 | Project Management | 90 | 7.2 | 5 | 1.76 | Initial vendor assessment for ASR (Automatic Speech Recognition) APIs.
VoiceVault - AI for Audio Transcription & Summarization (Meetings) | 2025-03-25 | LLM Development | 320 | 25.6 | 5 | 3.2 | Summarization model architecture research.
VoiceVault - AI for Audio Transcription & Summarization (Meetings) | 2025-03-25 | Data Engineering | 200 | 16 | 5 | 2.8 | Collecting sample meeting audio (anonymized).
VoiceVault - AI for Audio Transcription & Summarization (Meetings) | 2025-03-25 | UI/UX (Mock) | 70 | 5.6 | 3 | 800 | Interface for audio upload and summary display.
VoiceVault - AI for Audio Transcription & Summarization (Meetings) | 2025-03-25 | Testing & QA | 80 | 6.4 | 0 | 0 | (Not started)
VoiceVault - AI for Audio Transcription & Summarization (Meetings) | 2025-03-25 | Total Project Est: | 760 | 60.8 | 107 | 8.56 | Overall: On Track. Dataset Completion Target: 2025-07-05. Internal Alpha Testing Target: 2025-09-15.
VoiceVault - AI for Audio Transcription & Summarization (Meetings) | 2025-03-25 | [5 empty] | Finalization Report Target: 2025-11-30.
VoiceVault - AI for Audio Transcription & Summarization (Meetings) | 2025-04-25 | Project Management | 90 | 7.2 | 10 | 3.6 | Legal review for privacy compliance.
VoiceVault - AI for Audio Transcription & Summarization (Meetings) | 2025-04-25 | LLM Development | 320 | 25.6 | 10 | 10.4 | Fine-tuning of summarization model on meeting transcripts.
VoiceVault - AI for Audio Transcription & Summarization (Meetings) | 2025-04-25 | Data Engineering | 200 | 16 | 40 | 8 | Transcription data processing and alignment.
VoiceVault - AI for Audio Transcription & Summarization (Meetings) | 2025-04-25 | UI/UX (Mock) | 70 | 5.6 | 8 | 2.4 | Playback and editing features mockups.
VoiceVault - AI for Audio Transcription & Summarization (Meetings) | 2025-04-25 | Testing & QA | 80 | 6.4 | 1 | 1.2 | ASR accuracy testing across different audio qualities.
VoiceVault - AI for Audio Transcription & Summarization (Meetings) | 2025-04-25 | Total Project Est: | 760 | 60.8 | 320 | 25.6 | Overall: On Track. Dataset Completion Target: 2025-07-05. Internal Alpha Testing Target: 2025-09-15.
VoiceVault - AI for Audio Transcription & Summarization (Meetings) | 2025-04-25 | [5 empty] | Finalization Report Target: 2025-11-30.
VoiceVault - AI for Audio Transcription & Summarization (Meetings) | 2025-05-20 | Project Management | 90 | 7.2 | 15 | 5.2 | Stakeholder demonstrations of initial prototype.
VoiceVault - AI for Audio Transcription & Summarization (Meetings) | 2025-05-20 | LLM Development | 320 | 25.6 | 15 | 17.6 | Speaker diarization integration and performance tuning.
VoiceVault - AI for Audio Transcription & Summarization (Meetings) | 2025-05-20 | Data Engineering | 200 | 16 | 60 | 13.6 | Data pipeline optimized for real-time processing.
VoiceVault - AI for Audio Transcription & Summarization (Meetings) | 2025-05-20 | UI/UX (Mock) | 70 | 5.6 | 16 | 4 | Prototype development nearing completion.
VoiceVault - AI for Audio Transcription & Summarization (Meetings) | 2025-05-20 | Testing & QA | 80 | 6.4 | 3 | 2.4 | Summarization quality and coherence testing.
VoiceVault - AI for Audio Transcription & Summarization (Meetings) | 2025-05-20 | Total Project Est: | 760 | 60.8 | 535 | 42.8 | Overall: On Track. Dataset Completion Target: 2025-07-05. Internal Alpha Testing Target: 2025-09-15.
VoiceVault - AI for Audio Transcription & Summarization (Meetings) | 2025-05-20 | [5 empty] | Finalization Report Target: 2025-11-30.
VisionGuard - Deep Learning for Anomaly Detection (Manufacturing Defects) | 2025-03-01 | Project Management | 80 | 6.4 | 20 | 1.6 | Initial client requirements gathering for defect types.
VisionGuard - Deep Learning for Anomaly Detection (Manufacturing Defects) | 2025-03-01 | Deep Learning Dev. | 350 | 28 | 60 | 4.8 | Researching CNN/Transformer architectures for image classification.
VisionGuard - Deep Learning for Anomaly Detection (Manufacturing Defects) | 2025-03-01 | Data Engineering | 200 | 16 | 40 | 3.2 | Setting up image acquisition from production line (mock).
VisionGuard - Deep Learning for Anomaly Detection (Manufacturing Defects) | 2025-03-01 | UI/UX (Mock) | 50 | 4 | 10 | 800 | Visual defect reporting dashboard mockups.
VisionGuard - Deep Learning for Anomaly Detection (Manufacturing Defects) | 2025-03-01 | Testing & QA | 70 | 5.6 | 0 | 0 | (Not started)
VisionGuard - Deep Learning for Anomaly Detection (Manufacturing Defects) | 2025-03-01 | Total Project Est: | 750 | 60 | 130 | 10.4 | Overall: On Track. Dataset Completion Target: 2025-06-15. Internal Alpha Testing Target: 2025-08-01.
VisionGuard - Deep Learning for Anomaly Detection (Manufacturing Defects) | 2025-03-01 | [5 empty] | Finalization Report Target: 2025-09-30.
VisionGuard - Deep Learning for Anomaly Detection (Manufacturing Defects) | 2025-04-01 | Project Management | 80 | 6.4 | 40 | 3.2 | Weekly client check-ins.
VisionGuard - Deep Learning for Anomaly Detection (Manufacturing Defects) | 2025-04-01 | Deep Learning Dev. | 350 | 28 | 150 | 12 | Initial model training on a small dataset of 'good' vs 'bad' parts.
VisionGuard - Deep Learning for Anomaly Detection (Manufacturing Defects) | 2025-04-01 | Data Engineering | 200 | 16 | 100 | 8 | Image labeling process defined; initial 20% of dataset labeled.
VisionGuard - Deep Learning for Anomaly Detection (Manufacturing Defects) | 2025-04-01 | UI/UX (Mock) | 50 | 4 | 25 | 2 | Real-time defect highlight overlay design.
VisionGuard - Deep Learning for Anomaly Detection (Manufacturing Defects) | 2025-04-01 | Testing & QA | 70 | 5.6 | 2 | 1.2 | Accuracy testing for basic image recognition.
VisionGuard - Deep Learning for Anomaly Detection (Manufacturing Defects) | 2025-04-01 | Total Project Est: | 750 | 60 | 330 | 26.4 | Overall: On Track. Dataset Completion Target: 2025-06-15. Internal Alpha Testing Target: 2025-08-01.
VisionGuard - Deep Learning for Anomaly Detection (Manufacturing Defects) | 2025-04-01 | [5 empty] | Finalization Report Target: 2025-09-30.
VisionGuard - Deep Learning for Anomaly Detection (Manufacturing Defects) | 2025-05-01 | Project Management | 80 | 6.4 | 60 | 4.8 | Next phase planning for integration.
VisionGuard - Deep Learning for Anomaly Detection (Manufacturing Defects) | 2025-05-01 | Deep Learning Dev. | 350 | 28 | 250 | 20 | Model optimization for complex defect patterns. Achieved 92% detection rate on test set.
VisionGuard - Deep Learning for Anomaly Detection (Manufacturing Defects) | 2025-05-01 | Data Engineering | 200 | 16 | 160 | 12.8 | Dataset 70% complete. Annotation quality review in progress.
VisionGuard - Deep Learning for Anomaly Detection (Manufacturing Defects) | 2025-05-01 | UI/UX (Mock) | 50 | 4 | 40 | 3.2 | Alert system for critical defects defined.
VisionGuard - Deep Learning for Anomaly Detection (Manufacturing Defects) | 2025-05-01 | Testing & QA | 70 | 5.6 | 2 | 2.4 | False positive/negative rate analysis. Identified areas for model improvement.
VisionGuard - Deep Learning for Anomaly Detection (Manufacturing Defects) | 2025-05-01 | Total Project Est: | 750 | 60 | 540 | 43.2 | Overall: On Track. Dataset Completion Target: 2025-06-15. Internal Alpha Testing Target: 2025-08-01.
VisionGuard - Deep Learning for Anomaly Detection (Manufacturing Defects) | 2025-05-01 | [5 empty] | Finalization Report Target: 2025-09-30.
BioScan - Pattern Recognition for Disease Biomarker Identification | 2025-03-10 | Project Management | 100 | 8 | 5 | 2 | Ethical review board approval process initiated.
BioScan - Pattern Recognition for Disease Biomarker Identification | 2025-03-10 | Pattern Rec. Dev. | 400 | 32 | 60 | 4.8 | Feature engineering research for high-dimensional genomic/proteomic data.
BioScan - Pattern Recognition for Disease Biomarker Identification | 2025-03-10 | Data Engineering | 250 | 20 | 50 | 4 | Accessing secure clinical datasets (de-identified).
BioScan - Pattern Recognition for Disease Biomarker Identification | 2025-03-10 | UI/UX (Mock) | 60 | 4.8 | 10 | 800 | Visualization of biomarker correlations mockups.
BioScan - Pattern Recognition for Disease Biomarker Identification | 2025-03-10 | Testing & QA | 90 | 7.2 | 0 | 0 | (Not started)
BioScan - Pattern Recognition for Disease Biomarker Identification | 2025-03-10 | Total Project Est: | 900 | 72 | 145 | 11.6 | Overall: On Track. Dataset Completion Target: 2025-07-01. Internal Alpha Testing Target: 2025-09-01.
BioScan - Pattern Recognition for Disease Biomarker Identification | 2025-03-10 | [5 empty] | Finalization Report Target: 2025-11-01.
BioScan - Pattern Recognition for Disease Biomarker Identification | 2025-04-10 | Project Management | 100 | 8 | 10 | 4 | Regular meetings with medical experts.
BioScan - Pattern Recognition for Disease Biomarker Identification | 2025-04-10 | Pattern Rec. Dev. | 400 | 32 | 180 | 14.4 | Initial clustering and classification algorithms applied to pilot data.
BioScan - Pattern Recognition for Disease Biomarker Identification | 2025-04-10 | Data Engineering | 250 | 20 | 120 | 9.6 | Data harmonization and normalization across different clinical sites.
BioScan - Pattern Recognition for Disease Biomarker Identification | 2025-04-10 | UI/UX (Mock) | 60 | 4.8 | 30 | 2.4 | Interactive charts for pattern discovery.
BioScan - Pattern Recognition for Disease Biomarker Identification | 2025-04-10 | Testing & QA | 90 | 7.2 | 15 | 1.2 | Cross-validation setup for model robustness.
BioScan - Pattern Recognition for Disease Biomarker Identification | 2025-04-10 | Total Project Est: | 900 | 72 | 395 | 31.6 | Overall: On Track. Dataset Completion Target: 2025-07-01. Internal Alpha Testing Target: 2025-09-01.
BioScan - Pattern Recognition for Disease Biomarker Identification | 2025-04-10 | [5 empty] | Finalization Report Target: 2025-11-01.
BioScan - Pattern Recognition for Disease Biomarker Identification | 2025-05-10 | Project Management | 100 | 8 | 10 | 6 | Publication strategy for research findings.
BioScan - Pattern Recognition for Disease Biomarker Identification | 2025-05-10 | Pattern Rec. Dev. | 400 | 32 | 280 | 22.4 | Biomarker signature identification 70% confidence. Refining algorithms for higher specificity.
BioScan - Pattern Recognition for Disease Biomarker Identification | 2025-05-10 | Data Engineering | 250 | 20 | 190 | 15.2 | Integration with new data streams for expanded cohort.
BioScan - Pattern Recognition for Disease Biomarker Identification | 2025-05-10 | UI/UX (Mock) | 60 | 4.8 | 45 | 3.6 | Reporting module for medical practitioners.
BioScan - Pattern Recognition for Disease Biomarker Identification | 2025-05-10 | Testing & QA | 90 | 7.2 | 40 | 3.2 | Statistical validation of biomarker significance. Identified false positives.
BioScan - Pattern Recognition for Disease Biomarker Identification | 2025-05-10 | Total Project Est: | 900 | 72 | 630 | 50.4 | Overall: Minor Delay (Testing). Dataset Completion Target: 2025-07-15 (revised).
BioScan - Pattern Recognition for Disease Biomarker Identification | 2025-05-10 | [5 empty] | Internal Alpha Testing Target: 2025-09-15 (revised). Finalization Report Target: 2025-11-15 (revised).
AgroIntel - AI for Crop Health Monitoring (Drone Imagery) | 2025-03-01 | Project Management | 70 | 5.6 | 18 | 1.44 | Farm selection for pilot program.
AgroIntel - AI for Crop Health Monitoring (Drone Imagery) | 2025-03-01 | Visual Recognition Dev. | 300 | 24 | 50 | 4 | Initial research on multispectral image analysis techniques.
AgroIntel - AI for Crop Health Monitoring (Drone Imagery) | 2025-03-01 | Data Engineering | 180 | 14.4 | 30 | 2.4 | Setting up drone imagery acquisition protocols.
AgroIntel - AI for Crop Health Monitoring (Drone Imagery) | 2025-03-01 | UI/UX (Mock) | 50 | 4 | 2 | 800 | Farm map overlay with health indicators.
AgroIntel - AI for Crop Health Monitoring (Drone Imagery) | 2025-03-01 | Testing & QA | 60 | 4.8 | 0 | 0 | (Not started)
AgroIntel - AI for Crop Health Monitoring (Drone Imagery) | 2025-03-01 | Total Project Est: | 660 | 52.8 | 108 | 8.64 | Overall: On Track. Dataset Completion Target: 2025-06-20. Internal Alpha Testing Target: 2025-08-05.
AgroIntel - AI for Crop Health Monitoring (Drone Imagery) | 2025-03-01 | [5 empty] | Finalization Report Target: 2025-10-15.
AgroIntel - AI for Crop Health Monitoring (Drone Imagery) | 2025-04-01 | Project Management | 70 | 5.6 | 35 | 2.8 | Farmer feedback sessions.
AgroIntel - AI for Crop Health Monitoring (Drone Imagery) | 2025-04-01 | Visual Recognition Dev. | 300 | 24 | 120 | 9.6 | Deep learning model training for disease/pest detection on initial imagery.
AgroIntel - AI for Crop Health Monitoring (Drone Imagery) | 2025-04-01 | Data Engineering | 180 | 14.4 | 90 | 7.2 | Image pre-processing pipeline for cloud integration.
AgroIntel - AI for Crop Health Monitoring (Drone Imagery) | 2025-04-01 | UI/UX (Mock) | 50 | 4 | 2 | 2 | Alert system for localized disease outbreaks.
AgroIntel - AI for Crop Health Monitoring (Drone Imagery) | 2025-04-01 | Testing & QA | 60 | 4.8 | 10 | 800 | Initial accuracy assessment on basic plant health detection.
AgroIntel - AI for Crop Health Monitoring (Drone Imagery) | 2025-04-01 | Total Project Est: | 660 | 52.8 | 280 | 22.4 | Overall: On Track. Dataset Completion Target: 2025-06-20. Internal Alpha Testing Target: 2025-08-05.
AgroIntel - AI for Crop Health Monitoring (Drone Imagery) | 2025-04-01 | [5 empty] | Finalization Report Target: 2025-10-15.
AgroIntel - AI for Crop Health Monitoring (Drone Imagery) | 2025-05-01 | Project Management | 70 | 5.6 | 55 | 4.4 | Partner outreach for scaling.
AgroIntel - AI for Crop Health Monitoring (Drone Imagery) | 2025-05-01 | Visual Recognition Dev. | 300 | 24 | 200 | 16 | Model fine-tuning for specific crop types and regional diseases. Achieved 88% accuracy.
AgroIntel - AI for Crop Health Monitoring (Drone Imagery) | 2025-05-01 | Data Engineering | 180 | 14.4 | 150 | 12 | Dataset 75% complete. High-resolution imagery processing requires more resources.
AgroIntel - AI for Crop Health Monitoring (Drone Imagery) | 2025-05-01 | UI/UX (Mock) | 50 | 4 | 5 | 3.2 | Mobile application prototype for field data entry.
AgroIntel - AI for Crop Health Monitoring (Drone Imagery) | 2025-05-01 | Testing & QA | 60 | 4.8 | 30 | 2.4 | Field validation of detected anomalies. Confirmed some false positives.
AgroIntel - AI for Crop Health Monitoring (Drone Imagery) | 2025-05-01 | Total Project Est: | 660 | 52.8 | 475 | 38 | Overall: Minor Delay (Data Engineering). Dataset Completion Target: 2025-06-30 (revised).
AgroIntel - AI for Crop Health Monitoring (Drone Imagery) | 2025-05-01 | [5 empty] | Internal Alpha Testing Target: 2025-08-20 (revised). Finalization Report Target: 2025-10-31 (revised).
RoboNav - Reinforcement Learning for Autonomous Drone Navigation | 2025-03-15 | Project Management | 100 | 8 | 25 | 2 | Safety protocol definitions for drone testing.
RoboNav - Reinforcement Learning for Autonomous Drone Navigation | 2025-03-15 | RL Development | 450 | 36 | 400 | 5.6 | Simulation environment setup (Gazebo/Unity).
RoboNav - Reinforcement Learning for Autonomous Drone Navigation | 2025-03-15 | Data Engineering | 150 | 12 | 30 | 2.4 | Collecting environmental sensor data for simulation.
RoboNav - Reinforcement Learning for Autonomous Drone Navigation | 2025-03-15 | UI/UX (Mock) | 60 | 4.8 | 10 | 800 | Drone control and visualization dashboard mockups.
RoboNav - Reinforcement Learning for Autonomous Drone Navigation | 2025-03-15 | Testing & QA | 120 | 9.6 | 0 | 0 | (Not started)
RoboNav - Reinforcement Learning for Autonomous Drone Navigation | 2025-03-15 | Total Project Est: | 880 | 70.4 | 135 | 10.8 | Overall: On Track. Dataset Completion Target: N/A (simulated). Internal Alpha Testing Target: 2025-08-01 (sim).
RoboNav - Reinforcement Learning for Autonomous Drone Navigation | 2025-03-15 | [5 empty] | Finalization Report Target: 2025-11-30.
RoboNav - Reinforcement Learning for Autonomous Drone Navigation | 2025-04-15 | Project Management | 100 | 8 | 50 | 4 | Regulatory compliance for drone operations.
RoboNav - Reinforcement Learning for Autonomous Drone Navigation | 2025-04-15 | RL Development | 450 | 36 | 410 | 14.4 | Initial RL agent training for basic obstacle avoidance in simulation.
RoboNav - Reinforcement Learning for Autonomous Drone Navigation | 2025-04-15 | Data Engineering | 150 | 12 | 80 | 6.4 | Simulated environment data generation and logging.
RoboNav - Reinforcement Learning for Autonomous Drone Navigation | 2025-04-15 | UI/UX (Mock) | 60 | 4.8 | 30 | 2.4 | Real-time trajectory visualization and mission planning interface.
RoboNav - Reinforcement Learning for Autonomous Drone Navigation | 2025-04-15 | Testing & QA | 120 | 9.6 | 15 | 1.2 | Simulation environment verification.
RoboNav - Reinforcement Learning for Autonomous Drone Navigation | 2025-04-15 | Total Project Est: | 880 | 70.4 | 355 | 28.4 | Overall: On Track. Dataset Completion Target: N/A (simulated). Internal Alpha Testing Target: 2025-08-01 (sim).
RoboNav - Reinforcement Learning for Autonomous Drone Navigation | 2025-04-15 | [5 empty] | Finalization Report Target: 2025-11-30.
RoboNav - Reinforcement Learning for Autonomous Drone Navigation | 2025-05-15 | Project Management | 100 | 8 | 75 | 6 | Budget re-forecast based on compute usage.
RoboNav - Reinforcement Learning for Autonomous Drone Navigation | 2025-05-15 | RL Development | 450 | 36 | 420 | 24 | Complex path planning and dynamic obstacle avoidance in simulation. Achieved 70% success rate.
RoboNav - Reinforcement Learning for Autonomous Drone Navigation | 2025-05-15 | Data Engineering | 150 | 12 | 130 | 10.4 | Log data analysis for RL agent performance; identified data bottlenecks.
RoboNav - Reinforcement Learning for Autonomous Drone Navigation | 2025-05-15 | UI/UX (Mock) | 60 | 4.8 | 45 | 3.6 | Manual override and emergency landing protocol interfaces.
RoboNav - Reinforcement Learning for Autonomous Drone Navigation | 2025-05-15 | Testing & QA | 120 | 9.6 | 50 | 4 | Stress testing agent in adverse simulated conditions. Identified failure modes.
RoboNav - Reinforcement Learning for Autonomous Drone Navigation | 2025-05-15 | Total Project Est: | 880 | 70.4 | 600 | 48 | Overall: Slight Delay (RL Agent Robustness). Internal Alpha Testing Target: 2025-08-15 (revised sim).
RoboNav - Reinforcement Learning for Autonomous Drone Navigation | 2025-05-15 | [5 empty] | Finalization Report Target: 2025-12-15 (revised).